## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Smart Receipt Management and Extraction
|  |  | Legend: |  | Research |  |  |  |  | meeting |  |  |  |  | Submission |  |  |  |  | Implementation
Project start date: | 2023-10-11 |  |  |  | October | [20 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [28 empty] | March | [30 empty] | April
Scrolling increment: | 0 | time axis 2023-10-11 to 2024-05-01
Milestone description | Category | Start | Days | 2 | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Project Initiation
meeting with suppervisor | Meeting | 2023-10-11 | 1
research on project | Research | 2023-10-12 | 12
Draft proposal | Implementation | 2023-10-12 | 13
meeting with suppervisor | Meeting | 2023-10-25 | 1
Proposal finalisation | Implementation | 2023-10-26 | 16
Proposal submission | Deliverable - Milestone | 2023-11-11 | 1 | bar: 2023-11-11
Literature Review (LI)
Research for LI | Research | 2023-11-12 | 30
Draft LI | Implementation | 2023-12-12 | 15
meeting with suppervisor | Meeting | 2023-12-27 | 1
finalising LI | Implementation | 2023-12-28 | 16
submition LI | Deliverable - Milestone | 2024-01-13 | 1 | bar: 2024-01-13
Model Creation
Gather receipt data | Research | 2024-01-14 | 12
Developt receipt detection model | Implementation | 2024-01-14 | 7
Developt OCR | Implementation | 2024-01-21 | 5
Evaluate receipt extraction | Implementation | 2024-01-26 | 3
Finelising extraction model | Milestone | 2024-01-29 | 1 |  | 2024-01-29: 2
Meeting with suppervisor | Meeting | 2024-01-30 | 1
Server Side
Incorpore model | Implementation | 2024-01-31 | 5
Implement image preprocessing | Implementation | 2024-02-05 | 5
implement pfd processing | Implementation | 2024-02-10 | 3
Implement report generation | Implementation | 2024-02-13 | 5
Test Serside feature | Implementation | 2024-02-18 | 3
Finalise Server Side | Milestone | 2024-02-21 | 1 |  | 2024-02-21: 2
meeting with suppervisor | Meeting | 2024-02-22 | 1
Mobile App
Devellpot application front-end | Implementation | 2024-02-23 | 10
Implement image preprocessing | Implementation | 2024-03-04 | 4
Implement picture captaion feature | Implementation | 2024-03-08 | 5
Implement communication with server | Implementation | 2024-03-13 | 5
Implement user data correction feature | Implementation | 2024-03-18 | 5
Implement annalytics | Implementation | 2024-03-23 | 5
Implement receipt data export feature | Implementation | 2024-03-28 | 5
Test Mobile Application | Implementation | 2024-04-02 | 3
Finalizing Mobile Application | Milestone | 2024-04-05 | 1 |  | 2024-04-05: 2
meeting with suppervisor | Meeting | 2024-04-06 | 1
Final Report
Report draft | Implementation | 2024-04-07 | 14
meeting with suppervisor | Meeting | 2024-04-21 | 1
Finalising report | Implementation | 2024-04-22 | 5
Submeeting report | Deliverable - Milestone | 2024-04-27 | 1 | bar: 2024-04-27

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2023-11-05 |  |  |  |  | November | [20 empty] | December
Scrolling increment: | 5 | time axis 2023-11-10 to 2024-01-04
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
TITLE 1
Task 1 | Goal | Name | 25% | 2023-11-05 | 3
Task 2 | Milestone |  |  | 2023-11-10 | 1 | bar: F
Task 3 | Low Risk |  | 50% | 2023-11-02 | 10
Task 4 | Milestone |  |  | 2023-11-25 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2023-11-11 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-11-11 | 13
Task 2 | On Track |  | 50% | 2023-11-13 | 9
Task 3 | Low Risk |  | 33% | 2023-11-18 | 11
Task 4 | Milestone |  |  | 2023-11-20 | 1 | bar: M
Task 5 |  |  |  | 2023-11-21 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-11-20 | 4
Task 2 | Med Risk |  |  | 2023-11-23 | 14
Task 3 | On Track |  |  | 2023-12-08 | 6
Task 4 | Goal |  |  | 2023-12-12 | 3 | T: 2; W: 2; T: 2
Task 5 | Low Risk |  |  | 2023-11-11 | 19
TITLE 4
Task 1 |  |  |  | 2023-12-15 | 15
Task 2 |  |  |  | 2023-12-29 | 5
Task 3 | Milestone |  |  | 2024-02-09 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2023-11-05 |  |  |  |  | November | [20 empty] | December
Scrolling increment: | 5 | time axis 2023-11-10 to 2024-01-04
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-11-10 to 2024-01-04
TITLE 1
Task 1 | Goal | Name | 25% | 2023-11-05 | 3
Task 2 | Milestone |  |  | 2023-11-10 | 1 | bar: 2023-11-10
Task 3 | Low Risk |  | 50% | 2023-11-02 | 10
Task 4 | Milestone |  |  | 2023-11-25 | 1 | bar: 2023-11-25
Task 5 | Med Risk |  | 10% | 2023-11-11 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-11-11 | 13
Task 2 | On Track |  | 50% | 2023-11-13 | 9
Task 3 | Low Risk |  | 33% | 2023-11-18 | 11
Task 4 | Milestone |  |  | 2023-11-20 | 1 | bar: 2023-11-20
Task 5 |  |  |  | 2023-11-21 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-11-20 | 4
Task 2 | Med Risk |  |  | 2023-11-23 | 14
Task 3 | On Track |  |  | 2023-12-08 | 6
Task 4 | Goal |  |  | 2023-12-12 | 3 | 2023-12-12: 2; 2023-12-13: 2; 2023-12-14: 2
Task 5 | Low Risk |  |  | 2023-11-11 | 19
TITLE 4
Task 1 |  |  |  | 2023-12-15 | 15
Task 2 |  |  |  | 2023-12-29 | 5
Task 3 | Milestone |  |  | 2024-02-09 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one